SSEA (Social Science Education and Art)

Committee members: J Benjamin, M Cordova, P Martinez, T Timmers; Retired K Murdoff

WHAT IS SSEA?  A committee of volunteer SS staff and students determined to improve the identity of the Social Science Space visually. We work with the Campus Art committee and secure resources.

WHAT IS SSEA’S GOALS? The committee’s goal is to impart a visual identity for the Social Sciences using art as an aesthetic educational vehicle.

H I S T O R Y   TO  DATE

12 FALL: Brainstorm Meetings: Ideas & Goal Results:

- Mural (one wall)

- Framed poster-sized art of individual discipline icons or scenes

- Touch board for student ideas and graphic (entrance).

- Hanging mobile/banners from ceilings

- Specialized Lighting for art

12 WINTER: Placement of Art on walls? and  Funding?

Placement of Art: Committee met with Tom Madison (Graphic Design) for help in design/layout of project; Meeting results:

- Begin mural across SS office (east wall), wrap east on (south wall) interior hallway towards study corral, ending across from classroom 416.

- Touch screen across from Main office (idea found problematic)

- Individual discipline framed Poster-sized icons/scenes: west wall opposite map room and wrap toward 420 offices.

- Individual discipline framed Poster-sized icons/scenes in study corral area.

- Banners/hanging mobiles near elevator & west entrance (potential fire code violation)

Funding:

- Gathered list of Grant opportunities and deadlines.

- Tom offered help develop mural design, execution & paint. His expertise is murals.

12 SPRING: Content for project and Campus ART Committee Approval

What content will represent Soc. Sci. Art?

- SSEA Encouraged SS Faculty to share information about discipline movers and shapers, ideas, and icons. This referred to as “content dump” which represented all disciplines.

- Mural Design and execution becomes Phase 1 of SSEA Project Goals (resource found).

Proposal for Campus Art Committee Approval.

Content Dump was sent to  Tom Madison to mock up a mural idea for the meeting as evidence that we are a serious group seeking the art committee approval.

Granted Approval of project; Campus Art requested periodic checks on progress.

12 SUMMER Tom suggests a 199 class on “Designing Art for Public Spaces” using the SS as a client.

12 FALL “Designing Art for Public Spaces” lacks enrollment; is cancelled.

13 WINTER Art 199 Designing Art for Public Spaces class runs

- Class meets with SSEA and SS faculty discuss concepts and ideas with students.

- Students present first drafts of their work to SS for critique. Drafts display for feedback

- Revisions from feedback re-introduced to faculty.

- End of Winter Term. Students complete course.

13SPRING: NO MEETINGS

13FALL: Feedback results;

- more feedback on 4 drafts that may be viable; 3 are abandoned.  HERE WE ARE TODAY!

- does SS faculty have a specific  conceptual model to put forward as viable ?

IMPORTANT TIMING CONSIDERATIONS:

1) TWO students from the Winter 13 class are willing to work on revisions fall & maybe? Winter 14

2) Tom Madison will likely be gone Winter 14 so he cannot help students.

3) Students will need to execute/paint design in Spring and Summer 14.